lMhat;GnuvtþkñúgkmµviFI MS-Project

snµtfa Project X manTinñn½ydUcxageRkam³

Gantt Activity:

|  | Tasks | Task Description | Immediate Predecessors | Duration (Days) | Resources |
| --- | --- | --- | --- | --- | --- |
|  | 1 2 3 4 5 6 7 8 9 10 11 12 13 14 15 16 17 18 19 | Basic design Hardware design for A Hardware design for B Drawing for B Software specifications Parts purchase for B Parts purchase for A Drawings for A Installation drawings Software purchases Delivery of parts for A Delivery of parts for B Software delivery Assembly of A Assembly of B Test A Test B Final installation Final system test | - 1 1 3 3 3 2 2 2, 3 5 6 7 10 10, 12 4, 11 14 15 9, 16, 17 18, 13 | 10 8 6 4 2 4 4 5 5 5 5 3 3 1 5 2 3 8 6 | Dara Sok Sok Sok Dara Vuthy Vuthy Vuthy Thida Thida Dara Sok Dara Sok Sok Vuthy Vuthy Dara Sok |

Resources Table:

| Resources Name | Position | Standard Wage Rate Per Hour | O.T Rate Per Hour |
| --- | --- | --- | --- |
| Dara | Management | 5.0$ | 3.0$ |
| Sok | staff | 2.0$ | 1.0$ |
| Thida | staff | 2.0$ | 1.0$ |
| Vuthy | staff | 4.0$ | 2.0$ |

Project Working Time:

-Monday to Saturday

Morning

-7:00AM-11:00AM

Evening

-2:00PM-5:00PM

Project Start Date: 19-October-2007

-edayeRbIkmµviFI MS-Project cUr³

0-bBa©ÚlTinñn½ykñúgtaragxagelIeTAkñúg Sheet-View rbs; MS-Project

1-KNnary³eBlsrubrbs;KMeragTaMgmUl?

2-bgðaj Activity Ca Critical Path?

3-KNna Total Slack and Free Slack?

4-rkviFIedImI,bgðaj Report dUcxageRkam³

k-Cash flow report

x-Resources usage report

K-Who Does When report

X-View Network Diagram

g- View Task Usage

sMKal;

-rebobrk Total Slack and Free Slack

sßitenA Gantt Chart View. Click View –Click Table- Click Schedule

-rebobemIl Project Summary

sßitenA Gantt Chart View. Click View –Click Table- Click Summary